P9 Financial Management Report

April to December 2023

Executive Summary

2023/24 Capital Budget

A review of projects was carried out for P9 resulting in a forecast of £23.6m, against a budget of £29.4m, an underspend of £5.8m which is 20% of the revised budget. This is an increase from P8 of £0.450m.

The capital budget for 2023/24 of £20.578m was approved by both COMB (January 2023) and the PCC (February 2023). Since then, the following approvals were made resulting in a current budget of £29.406m.

|  | £ |  |  |
| --- | --- | --- | --- |
| Capital budget 23/24 | 20,578,000 | Approved by COMB January 23 |  |
| Roll forward from 22/23 to 23/24 | 7,792,000 | Approved by COMB February 23 |  |
| Total Approved Capital Budget 23/24 | 28,370,000 |  |  |
| Additional Budget Approvals /Increases During 23/24 |  | Sources of Funding | Dept |
| Automatic Number Plate Recognition (ANPR) ADSL | 34,620 | Transfer from Drugs fund to capital | Other |
| KPC Accommodation block - fire stopping | 48,000 | Revenue transfer to capital | Estates |
| Air con Maidstone & Tonbridge | 90,000 | Revenue transfer to capital | Estates |
| STA Fire Compartmentation | 529,126 | Revenue transfer to capital | Estates |
| Eastern Regions Special Operations Unit (ERSOU) | 72,525 | Revenue transfer to capital | Other |
| Digital Forensic Unit (DFU) Platform | 42,500 | Transfer from Proceeds of Crime Act (POCA) fund to be made | IT |
| Total Revenue to Capital Transfers | 816,771 |  |  |
| Ashford re-modelling - additional cost approved | 195,000 | within capital reserve - utilising underspends from other projects | Estates |
| Zenith Coldharbour - automated door | 11,339 | External contribution from Kent Fire and Rescue Service | Estates |
| ANPR replacement | 12,890 | External contribution - Insurance funds | ANPR |
| Total External Contributions | 24,229 |  |  |
| Current Capital Budget at P8 | 29,406,000 |  |  |

| Budget Transfers from One Project to Another - "In Year Approvals" |  |  |  |
| --- | --- | --- | --- |
|  | £ |  |  |
| From Digital Interview Recording (DIR) to Integrated Communications Control System (ICCS) | 60,000 | DIR budget reduced/ICCS budget increased | IT |
| From DFU to Kent Data Centre (KDC) | 60,000 | DFU budget reduced/KDC budget increased | IT |
| From Zenith to Ashford re modelling | 3,106,000 | Zenith budget reduced/Ashford budget increased | Estates |
| From Zenith to Sutton Road Phase 1 | 522,000 | Zenith budget reduced/Sutton Road budget allocated | Estates |
| From Folkestone roof to Kent Police College (KPC) & Firearms roof budget | 149,146 | Folkestone budget reduced/KPC & Firearms increased | Estates |

Historically, over the last three financial years, the capital budget has underspent by an average of 38% (20/21 -38%, 21/22 -47%, 22/23 -29%).

Prior year data suggests there is potential that this underspend will increase; however, Stage 1 projects that will not be progressed to Stage 2 have already been considered within this P9 forecast leaving the approved projects to continue with implementation.

Regarding capital receipts, a budget of £10.47m was set for 2023/24 and we have achieved sales totalling £2.2m to date, with a further £1.0m forecast. It should be noted that with the forecast and budget for Sutton Road removed, capital receipts of £3.2m are still exceeding the remaining budget. The impact of the forecast reduction in total capital receipts means the funding gap is larger within the capital programme and the cost of borrowing will impact upon the revenue budget. It is estimated that there will be a rollover of £5.0m as an additional pressure in the 2024/25 financial year.

2023/24 Revenue Budget

The revenue budget is £386.2m, and the forecasted full year revenue as at P9 remains at £384.7m, which would result in a full year underspend of (£1.5m). This is a nil movement in the month.

Key Revenue Drivers Over the Year

The current forecast reflects the best estimate at this point in time as to where we will finish the year, but it is accepted there will be movement and the risk and opportunities log reflects our understanding of what could move the forecast going forward.

- The police officer attrition is forecast as per the table below and was agreed at the volume recruitment meeting on 11th December 2023. December attrition at 27 was as per expectations maintaining the year average of 27, and the latest profile and comparison can be seen below.

- Closing projected establishment at 4,122 FTE is on budget and total headcount for Police at the end of the year is forecast to be 4,223 compared to required PUP uplift headcount requirement of 4,218. This profile enables Kent Police to hit the PUP maintenance target.

| Police numbers | Actual / Forecast |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Period | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |
| Attrition - Actual / Forecast | 29 | 26 | 29 | 27 | 23 | 36 | 22 | 28 | 27 | 27 | 27 | 27 |
| Forecast attrition last mth | 29 | 26 | 29 | 27 | 23 | 36 | 22 | 28 | 27 | 27 | 27 | 27 |
| Joiners - Actual / Forecast | 0 | 0 | 0 | 16 | 0 | 110 | 0 | 0 | 0 | 55 | 0 | 101 |
| Transfers - Actual / Forecast | 1 | 1 | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 |
| Forecast Joiners & Transfers last mth | 1 | 1 | 1 | 16 | 0 | 114 | 0 | 0 | 0 | 55 | 0 | 105 |
| Closing FTE | 4129 | 4104 | 4076 | 4065 | 4042 | 4120 | 4098 | 4071 | 4044 | 4072 | 4045 | 4123 |

- The cost of a Police leaver in the month has increased from prior month as the profile contained 7 leavers above the rank of constable. The average annual cost of a Police leaver (including on-costs) for the 9 months is now £58.9k against the budget of £59.8k, both of which reflect the 7% pay rise. The forecast for current year has been updated to reflect this change in trend although the average cost going forward is now higher due to the 7% pay award from September.

| Police pay - average leaver cost | Actual / Forecast |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Period | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |
| Month Actual / Forecast | £55,581 | £55,122 | £59,818 | £51,649 | £59,120 | £62,744 | £62,828 | £54,681 | £68,007 | £60,720 | £60,720 | £60,720 |
| Year to Date | £55,581 | £55,366 | £56,892 | £55,614 | £56,221 | £57,596 | £58,190 | £57,748 | £58,887 |  |  |  |
| Budget | £58,705 | £58,705 | £58,705 | £58,705 | £58,705 | £59,879 | £59,879 | £59,879 | £59,879 | £59,879 | £59,879 | £59,879 |

- The full year PCSO pay forecast incorporates the change to 101.5 FTE as a result of the NHP model going live in June 23 and this is reflected in the Vacancy Factor table below. Please note that PCSO’s show higher in first 2 months due to the new structure not going live until June, the large reduction in January 24 is the result of a planned intake.

- PSE (excluding PCSO’s) vacancies are currently at 8.9%, down on last month and impacted by 35 delimited posts in the FCIR, and a continued downward trend to 8.1% is forecast by year end. This is based on an assumption of 13 joiners and 11 leavers per month. It is interesting to note the potential positive impact of the 7% pay award; in the first 6 months of the year PSE force funded other went from 15.8% to 14.8% (1% drop) whereas for the second half of the year it is forecast to go from 14.8% to 12.8% so in fact retention/recruitment has improved since the pay award.

- For 2023/24, the budget has been set at an average of 9.6% being 11% for all departments other than FCIR, IMU and Custody which were set at 5%. This is based on a blended approach, assuming a higher vacancy rate at the beginning of the financial year and then reducing down by year end. The table below shows the vacancy rate % forecast for 23/24. For reference, the vacancy factor equates to roughly +/- £1.0m p.a. for every 1% above or below budget.

| Vacancy Factor | Actual / Forecast |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Period | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |
| FCIR | 12.4% | 6.3% | 1.9% | 3.8% | 0.4% | (1.3%) | 0.8% | 3.2% | (4.6%) | (2.2%) | (5.7%) | (3.8%) |
| IMU | (16.4%) | (11.6%) | (12.8%) | (11.2%) | (10.6%) | (8.2%) | (5.4%) | (3.9%) | (1.9%) | 0.2% | (11.7%) | (9.6%) |
| DDO | (1.5%) | (7.4%) | (6.6%) | (6.5%) | (4.3%) | (1.6%) | 1.1% | 3.3% | (1.0%) | (0.1%) | 0.7% | (5.3%) |
| PCSO's | 62.1% | 63.5% | 11.0% | 16.4% | 23.4% | 27.4% | 30.1% | 30.9% | 31.0% | 13.2% | 13.2% | 13.2% |
| PSE Force Funded other | 15.8% | 15.5% | 15.1% | 15.2% | 15.0% | 14.8% | 14.2% | 13.6% | 13.2% | 13.1% | 13.0% | 12.8% |
| PSE (excl PCSO, Ext, PCC, RC) | 12.6% | 11.4% | 10.3% | 10.8% | 10.3% | 10.1% | 10.3% | 10.4% | 8.9% | 9.4% | 8.1% | 8.1% |

- The vacancy factor on PSE Force Funded other line has decreased again from the previous month. The forecast going forward still assumes a continued reduction in the overall vacancy rate acknowledging that it is still high.

- The negative vacancy rates for FCIR, IMU and DDO are due to higher than establishment staffing, and these have tended to be in the months which experience peak demand. In respect of the FCR and IMU it should be noted that the plan was to be above establishment for the peak Summer months and under in other months. However, the recruitment profile in both areas now show as over establishment for the majority of the year which is not sustainable and will add a significant cost pressure if repeated in 24/25.

- In respect of North Kent PFI, a £1.7m overspend has been included as a forecast cost for legal/professional/advisory/remedial costs. This is subject to further revision as the project is now entering a new phase which will have both up and downsides.

Revenue Movement in Month

The forecast at P8 was £384.7m and at P9 it remains at £384.7m, which is a nil movement in the month.

Key movements are as follows:

- £0.4m Police and PSE pay auto enrolment impact as previously reported as Risks

- (£0.4m) PSE vacancy factor benefit previously reported as an Opportunity

Revenue Forecast Full Year Summary

The total outturn full year revenue underspend is (£1.5m). The main reasons behind this are:

- (£3.1m) saving on PSE pay due to:

  - (£0.6m) saving on PSEs that are on maternity leave made up of a saving of (£0.9m) and an associated cost pressure estimated at £0.3m. On average there are 49 members of staff on maternity leave per month, each at an average reduction in monthly pay of £1.6k. The effect of maternity leave has been incorporated in the 2024/25 budget.

  - (£2.4m) forecast underspend due to:

    - (£2.2m) higher than budgeted vacancy factor and delimiting of vacant posts

    - (£0.3m) over achievement on PCSO saving

    - £0.1m Pension auto enrolment has increased costs as 23 PSE’s re enrolled have stayed in the pension scheme

  - (£0.1m) Essex recharges to Kent currently tracking below budget due to a high vacancy rate in Essex too

- 0.3m overspend on Police Pay is forecast due to:

  - (£1.4m) saving on Police officers that are on maternity leave, on average there are 44 officers on maternity leave per month, at an average reduction in pay of £2.6k. The effect of maternity leave has been incorporated in the 2024/25 budget.

  - £0.7m unbudgeted adjusted holiday pay, which relates to the “Bear Scotland” ruling where holiday pay calculations should also include overtime, unsocial hours, acting up etc and not just basic pay

  - £0.5m increase in costs due to reduced attrition compared to the assumption made at budget setting in September 2022 and increased joiners

  - £0.3m Pension autoenrollment impact has increased costs as 54 officers re enrolled have stayed in the pension scheme

  - £0.2m relates to various other miscellaneous items

- £0.3m Police overtime overspend mainly due to vacancies which need to be covered to cover SLA requirements, abstractions, and training. Main areas impacted are Firearms, County Lines & Gangs and FCIR

- £0.7m PSE overtime overspend mainly due to the FCIR which had a number of vacancies and a number of new recruits who were in training, this has been completed which is now evidenced by reducing overtime

- £0.3m other variances including:

  - £1.7m overspend forecast in relation to Op Mercury (PFI) costs

  - £0.4m cost relating to Zenith, of which the majority is £0.6m for an estimated in-year reduction in cashable savings as there won’t be reduced usage at Sutton Road until at least P10, caused by delays in the moves to Ashford and Coldharbour, offset by one-off savings in relation to these delays (Appendix E for example)

  - £0.2m insurance cost increase assumption due to analysis of prior year actuarial assumptions and the inflationary impact on the cost of claims

  - £1.6m missed savings - see savings section for further information

  - £0.4m Estates and IT costs move to Sutton Road.

  - £0.5m Police Pension Injury and ill health provision based on the increased volumes and level of successful appeals

  - £0.9m Allard payments above that provided for in the budget

  - £0.2m for increased costs of implementing pension remedy (McCloud - in line with national guidance)

  - £0.1m increase in external recruitment centres based on updated recruitment profile

  - (£0.6m) council tax surplus

  - (£0.5m) budget assumption change on Critical National Infrastructure funding.

  - (£0.2m) reduction in vehicle insurance partially offset by increases in employee and premises insurances

  - (£1.3m) Estates underspend driven largely by one-off refunds of business rates following successful appeals

  - (£0.5m) the latest KCC Statement forecasts additional interest receivable from investments as a result of interest rate increases this year

  - (£0.1m) Transport saving on fuel in the first 6 months due to the earlier reduction in fuel prices compared to budget setting in September 22 and increased insurance recoveries offset by increased costs of parts and outsourcing

  - (£0.7m) underspend on IT project revenue in line with previous years and an underspend against National Law Enforcement Data Service (NLEDS)

  - (£0.3m) Training reductions from revised Strategic Training Needs Analysis (STNA) exercise and agreed delay to load vest issue to officers until new year

  - (£0.2m) additional contributions to capital in 22/23 have led to a lower Minimum Revenue Payment (MRP) in 23/24 as planned

  - (£1.3m) costs on externally funded, regional funded and investment funded activities offset by income including (£0.3m) of Mutual aid, (£0.1m) additional camera safety income, (£1.4m) Op Safeguard, £0.1m additional Gatwick hub costs, £0.3m additional ERSOU and SEROCU following revised updates received

2023/24 Risk and Opportunities

| Risks as at P9 |  |  |  |
| --- | --- | --- | --- |
| Cost centre area | Amount £ | Description | Level |
| Forensics | 50,000 | Forensic analysis costs could come under pressure due to contract negotiation requests from suppliers currently under review | High |
| Police Pension | 434,000 | In relation to pension immediate detriment - accrual raised on the assumption that funding will be received for this year’s costs to date - no formal notification from the Home Office of this happening | Low |
| Health Services | TBC | Potential change to payment method of Consultant (IR35). Expected invoice payments in 2023/24 of circa £120k so liability could be £60k. Also could be retrospectively enforced to 2017 | Med |
| Ashford | 100,000 | Additional works to facilitate office / Team moves | High |
| Insurance | TBC | Insurance is subject to a year end valuation. Potential risk that additional provision required based on an actuarial revaluation | Low/Med |
| Sub Total | 584,000 |  |  |
| Opportunities as at P9 |  |  |  |
| Cost centre area | Amount £ | Description | Level |
| Police Pensions | (703,000) | When the McCloud remedy legislation is enacted, it is possible the immediate detriment enhancements may be reimbursed to Kent Police though the Police Pension Fund. No notification received from the Home Office to date- further information anticipated in Jan 24 | Med/High |
| Estates | (100,000) | As per YTD analysis and historic trends, estates have potential to underspend. Noting here, despite the raising of significant PO's in P9, there is still a potential opportunity to be firmed up in coming months as spend trends emerge and decisions made re Fire doors | Med |
| Gatwick Hub | (60,000) | Q2 update received which infers reduction in costs compared to previous forecasts however this is dependent on cost of national operations P7-12 and subject to receipt of grant increase for pay award. | Low |
| Insurance | TBC | Insurance is subject to a year end valuation. Potential opportunity that less provision required based on an actuarial revaluation | Low/Med |
| Sub Total | (863,000) |  |  |

CFO Summary

The forecast remains as per last month and has remained stable for the past 3 periods. Whilst several risk and opportunities remain open, it is my view that at this point in time they are largely balanced.

In respect of the savings target for 24/25, it has reduced to £7.291m based on an increased precept of £13. A budget report detailing this along with a savings plan was taken to COMB on the 16th January 2024 and agreed. The Police and Crime Panel takes place on the 6th February 2024 where this will be confirmed (subject to panel approval).

It is important to note when you view the MTFP section below that future years remain challenging and decisions taken this year have been taken intentionally to balance the budget for 24/25 whilst awaiting potential changes to the operating environment in the next 12 months. Therefore, a number of savings that would’ve delivered structural permanent recurring savings have been deferred in lieu of this. If the funding changes don’t come in the next 12 months, or they do and aren’t beneficial or sufficient then those savings will have to be delivered for the 25/26 budget onwards.

Cashflow

Cashflow borrowing increased by a further £2.5m in December. This means that to date loans totalling £19.5m have been taken with redemptions falling in February and March 2024 at interest rates of circa 5.4%. Interest and brokerage for the current loans will be a cost to revenue of circa £400k.  Further cashflow loans will be required before the end of this financial year, continuing up to July 2024 when the large pension top-up grant of around £35m is received. As interest rates are like to remain at current levels in the short term, the interest costs will result in continuing pressure on the revenue budget.

Savings

The savings target for the year is £14.1m and at P9 the forecast includes an estimate that circa £1.8m will not be achieved.

MTFP 2024/25 to 2028/29

The MTFP has been updated as part of 24/25 budget setting. The key assumptions and headline figures can be seen below. What can be seen very clearly is that for every year going forward unless the funding increases then there will be a significant financial challenge necessitating in a savings requirement. The majority of this is due to the differential between the assumed increase in income and the assumed increase in staff costs via pay awards and increments.

The use of one-off savings is not sustainable so is only appropriate for 2024/25. Thereafter, there is a need for structural permanent recurring savings.

|  | Income/Cost Movement versus Prior Year |  |  |  |
| --- | --- | --- | --- | --- |
| Description | 2025/26 | 2026/27 | 2027/28 | 2028/29 |
|  | £000 | £000 | £000 | £000 |
| Tax base increase assumption 1.1% growth pa | -1,928 | -1,988 | -2,050 | -2,114 |
| Precept increase assumption 2% pa | -3,438 | -3,544 | -3,655 | -3,770 |
| Council tax surplus | -322 | 0 | 0 | 0 |
| 1% grant increase assumed pa | -2,238 | -2,260 | -2,283 | -2,306 |
| 2% pay award officers and staff assumed pa | 8,151 | 8,308 | 8,524 | 8,695 |
| Increments officers | 3,570 | 3,641 | 3,714 | 3,788 |
| Increments staff | 1,000 | 1,020 | 1,040 | 1,061 |
| Sub Total | 4,795 | 5,177 | 5,290 | 5,354 |
| One-off savings to be found following year | 2,219 | 0 | 0 | 0 |
| Inflation assumed at 2% increase pa | 572 | 636 | 653 | 670 |
| Minimum Revenue Provision based on capital plan as per Appendix C (note this does not include any major projects such as Folkestone or Canterbury) | 1,450 | 393 | 265 | 317 |
| Revenue to capital transfer | 1,000 | 1,000 | 1,000 | 1,000 |
| Digital forensics | 709 | 291 | 0 | 0 |
| Other | -1,750 | -856 | -811 | -866 |
| Op Magenta closure | 0 | 0 | 1,212 | 0 |
| Sub Total | 4,200 | 1,464 | 2,319 | 1,121 |
| Grand Total (savings required in year) | 8,995 | 6,641 | 7,609 | 6,475 |

Jonathan Castle CFO

##### Table 1: Revenue Forecast Outturn

| Subjective Category | Full Year Budget | Full year Forecast Spend | Forecast Variance |
| --- | --- | --- | --- |
|  | £'000 | £'000 | £'000 |
| Police Pay | 245,845 | 246,087 | 242 |
| PSE Pay | 104,332 | 101,321 | (3,011) |
| Other Pay Costs | 16,917 | 17,899 | 982 |
| Total Pay | 367,094 | 365,307 | (1,787) |
| Police Overtime | 5,390 | 5,653 | 263 |
| PSE Overtime | 1,190 | 1,813 | 623 |
| Total Overtime | 6,580 | 7,466 | 886 |
| Premises | 25,756 | 21,879 | (3,877) |
| Transport | 9,488 | 9,334 | (154) |
| Supplies & Services | 24,756 | 31,312 | 6,556 |
| Third Party Payments | 10,143 | 9,972 | (171) |
| Bad & Doubtful Debts | 0 | 0 | 0 |
| Total Running Expenses | 70,143 | 72,497 | 2,354 |
| Capital financing and contributions | 3,040 | 3,346 | 306 |
| Pension Administration Costs | 0 | 0 | 0 |
| Expenditure Sub-Total | 446,857 | 448,616 | 1,759 |
| Income |  |  |  |
| Sales, Fees, Charges & Rents | (4,696) | (7,563) | (2,867) |
| Interest / Investment Income | (685) | (1,321) | (636) |
| Reimbursed Services | (31,859) | (36,351) | (4,492) |
| Transfers to Revenue and Capital Reserves | (1,057) | 1,771 | 2,828 |
| Overseas Funding / Partnership Funding | (22,336) | (20,389) | 1,947 |
| Total Income | (60,633) | (63,853) | (3,220) |
| Overall Total | 386,224 | 384,763 | (1,461) |

##### Table 2: Reserves Position

| Usable Reserves | Reserves as at 1st April 2023 £'000 | Reserves Budget 2023/24 £'000 | Approved Movement in Year £'000 | Unders/Overs £'000 | Reserves as at 31st March 2024 £’000 |
| --- | --- | --- | --- | --- | --- |
| Non Earmarked |  |  |  |  |  |
| General Fund | 11,550 | 0 | 0 | 347 | 11,897 |
| Earmarked |  |  |  |  |  |
| Insurance | 2,969 | 0 | 0 | 0 | 2,969 |
| Capital Funding from Revenue | 0 | 1,000 | 4,295 | 0 | 5,295 |
| Capital Expenditure | 0 | (1,000) | (4,295) | 0 | (5,295) |
| Capital Contributions Unapplied Reserves | 114 | 0 | 0 | 0 | 114 |
| Budget Support | 8,687 | (2,057) | (1,425) | 1,461 | 6,666 |
| Op Brock/Stack Contingency Reserve | 1,078 | 0 | 0 | 0 | 1,078 |
| OPCC Budget Support | 1,157 | 0 | 0 | 0 | 1,157 |
| ERSOU Property Maintenance Fund | 93 | 0 | 0 | (13) | 80 |
| PFI Residual Value Reserve | 834 | 0 | 0 | 0 | 834 |
| Total Earmarked | 14,932 | (2,057) | (1,425) | 1,448 | 12,898 |
| Grand Total | 26,482 | (2,057) | (1,425) | 1,795 | 24,795 |

##### Table 3: Capital Budget

| Department | Revised Capital Budget | Spend to 31/12/23 | Forecast to 31/3/24 | Variance -(underspend) vs overspend | % of Budget Spent YTD | Estimated rollover requirement |
| --- | --- | --- | --- | --- | --- | --- |
|  | £'000 | £'000 | £'000 | £'000 | % | £'000 |
| IT Department (including Kent Data centre) | 5,879 | 2,328 | 4,885 | -994 | 40% | 1,189 |
| Estate Department | 2,866 | 449 | 1,478 | -1,388 | 16% | 1,037 |
| Estates Zenith building works including Sutton Rd | 6,047 | 4,485 | 4,944 | -1,103 | 74% | 0 |
| Estates backlog Capital | 4,181 | 1,104 | 1,338 | -2,843 | 26% | 2,798 |
| Transport | 4,023 | 2,876 | 4,018 | -5 | 71% | 0 |
| ANPR Department | 255 | 169 | 194 | -61 | 66% | 0 |
| Other - Plant & Equipment | 1,092 | 802 | 1,108 | 16 | 73% | 0 |
| Ashford Re-Modelling | 4,864 | 5,059 | 5,380 | 516 | 104% | 0 |
| Project Zenith Other costs - Open Zone furniture | 199 | 184 | 213 | 14 | 92% | 0 |
| Totals | 29,406 | 17,456 | 23,558 | -5,848 | 59% | 5,024 |

##### Table 4: Cashflow Forecast